## Sample Cleanup Plan
Step | Getting Started | Step | Publicity & Communications | Category | Step | Logistics | Step | Volunteer Recruiting | Step | Fundraising | Step | Supplies | Step | Recognition & Celebration
1 | Form a steering committee of like-minded people. | 1 | Write and distribute a press release to local media outlets and websites |  | 1 | Identify and prioritize your cleanup routes. Match the size of each cleanup area with an appropriate number of volunteers. See table below for sample cleanup route plan. | 1 | Contact local community groups (scouts, civic groups, houses of worship, sports organizations) to recruit volunteers. | 1 | Contact local businesses for donations. Offer sponsorship opportunities on tee shirts, social media, or website. | 1 | Obtain trash bags. In most cases, your local DPW will donate. If not, contact KMB. Determine whether you plan to provide gloves or trash-grabber tools. | 1 | Consider hosting a post-cleanup celebration.
2 | Meet with Town Manager, Mayor, and/or DPW director to get their buy-in and support. Seek out partners from the local business community too. | 2 | Create social media pages (Facebook page, Instagram and/or Twitter) |  | 2 | Determine where volunteers will meet and how you will assign cleanup routes (centralized location or multiple locations, depending on size of your event). | 2 | Reach out to local school administrators. | 2 | Set up a dedicated fundraising account with your municipal government or at a local bank. | 2 | Make sure your tee-shirt order in finalized 2-3 weeks prior to your event to ensure they are delivered in time. Contact KMB for discounted pricing. | 2 | Thank your volunteers through email, letter to editor, cable access TV, and social media channels.
3 | Set a date for your cleanup event. We suggest the last Saturday in April of each year. | 3 | Create posters/flyers that can be posted in local businesses, town buildings, churches, and schools |  | 3 | Determine who will remove trash bags and other debris at the conclusion of your cleanup. Usually, this is done by local DPW or a local waste hauler donates its services. | 3 | Reach out to local businesses. | 3 | Be sure to publicly thank sponsors on social media channels and with a personalized thank you note. | 3 | If you're hosting a post-cleanup celebration, make sure you have food and drink. Try to offer eco-friendly options by avoiding single-use plastic and/or offering recycling bins. | 3 | Send a personal note to your business sponsors and municipal partners.
4 | Determine if you will have a post-cleanup celebration and appoint a sub-committee to manage this event. | 4 | Try to get announcement on town or city website, newsletter, or utility bills. Post an article in local school newsletters. |  | 4 | Appoint "cleanup captains" who will manage and coordinate volunteers in particular geographic zones on the day of the cleanup. | 4 | Create an online registration site to make it easy for people to sign up. Google Docs is a free resource that works well. |  |  |  |  | 4 | Send confirmation/thank you letters for all donations
5 | Determine what expenses you will incur and how you will pay for them. | 5 | Consider hosting a show or creating a brief public service announcement on your local cable access TV. |  | 5 | Contact police dept. and EMTs to see if they can help with traffic and public safety. | 5 | Have a mechanism to confirm volunteer registrations and an email address and/or phone number they can use to contact you. |  |  |  |  | 5 | Take your efforts to the next level and reach out to KMB to learn about the benefits of launching a local KMB chapter.
6 | Keep meeting minutes with action items to ensure progress is made each month. | 6 | Post a message on the local cable access TV "scroll." |  | 6 | Determine whether you want to separate recyclables or not. If so, determine who will process the recyclables and ensure volunteers know what can be recycled. | 6 | Write and distribute safety procedures prior to your cleanup and train cleanup captains (see sample on KMB website).
7 | Conduct a litter index to prioritize areas most in need of cleanup. Contact Keep Massachusetts Beautiful (KMB) for more information on how to conduct the Litter Index. | 7 | Get your event listed on local media websites, such as wickedlocal.com or patch.com.
|  | 8 | Determine if you plan to offer tee shirts to volunteers. If so, reach out to local businesses to sell sponsorships. Contact KMB for special discounted pricing on tee shirts.

## Sample Cleanup Routes
Precinct # | Street or Location | Boundaries | Distance in Miles | # of Volunteers Needed or Assigned | Assigned Group | Volunteers in Group | Safety Issue? | Notes
1 | School St. | Plymouth St to Otis Street | 0.75 | 8 |  |  | yes
1 | West St. | Route 495 to Douglas Drive | 0.75 | 8 |  |  | yes | police escort?
1 | West St. | Douglas Drive to Old Farm Road | 1.5 | 6 |  |  | yes
1 | Gilbert St. | West St. to Otis Street | 1 | 6 |  |  | no
1 | Gilbert St. | Otis Street to Norton Line | 0.5 | 4 |  |  | no
1 | Old Elm St | entire st., including dirt road near entrance off School | 0.5 | 4 |  |  | no
1 | Balcolm St. | Jewell St to Otis | 0.5 | 4 |  |  | no
1 | Balcolm St. | Jewell St. to Gilbert | 0.5 | 4 |  |  | no
1 | Williams St. | Old Elm to Williams St. bridge | 0.75 | 6 |  |  | no
1 | Otis St. | Gilbert St. to baseball fields | 0.5 | 4 |  |  | no
1 | Plain St. | West to N. Attleboro line | 0.5 | 4
1 | South St. | Barton Rd to Grove St. | 0.5 | 4 |  |  | no
62
Precinct # | Street or Location | Boundaries | Distance in Miles | # of Volunteers Needed or Assigned | Assigned Group | Volunteers in Group | Safety Issue? | Notes
2 | South Main St. | East St. to Fruit St. | 1 | 4 |  |  | no
2 | School St. | Route 140 to Plymouth St | 0.75 | 16 | Green Earth Hornets |  | yes | MEMA
2 | School St. | East Side of 140 to West Street | 0.5 | 4 |  |  | yes | I have a group assigned to intersection of School and 140 (east side of 140)
2 | South Main St. | Fruit St. to Norton Line | 1.25 | 6 |  |  | yes
2 | South Common | South common/Town Hall area | 0.25 | 0 | Republican Party | 6 | no | they are all set
2 | Spring St. | South Main to School St., including Kingman's Pond | 0.75 | 6 |  |  | yes
2 | Bike Path | entire path | 2 | 8 | Cub Scout Pack 13 Joe Milani | 20 | no
2 | Willow St | School St. to South Main | 0.75 | 6 |  |  | no | the area near Spring Street is a mess
2 | Oak St. | Elm St. to town line | 0.75 | 4 |  |  | no
2 | Fruit St. | Stillbrook Lane to Short St. | 0.5 | 4 |  |  | no
2 | Elm Street | Otis Street to Norton Line | 1.5 | 6 |  |  | no
2 | Animal Shelter Road | off Fruit St. | 0.5 | 2 |  |  | no
2 | Reservoir Street | South Main to Columbine | 0.5 | 6
72
Precinct # | Street or Location | Boundaries | Distance in Miles | # of Volunteers Needed | Assigned Group | Volunteers in Group | Safety Issue? | Notes
3 | East St. | Route 106 (flint farm) to Dustin Court | 1 | 8 |  |  | no | includes East Common
3 | Mill St. | Norton Line to East Street | 1.25 | 8 |  |  | yes
3 | Branch St. | Ware st. to bike path | 0.5 | 6 |  |  | no | good for little kids
3 | Essex St. | Ware st. to Mill st. | 0.5 | 4 |  |  | no
3 | Ware St. | J/J to East St | 0.25 | 4 | Girl Scouts |  |  | a group is assigned to the very last stretch of Ware from the J/J parking lot up East St. and the Mansfield Green
3 | Ware St. | East St. to Marie Streese Conservation | 0.75 | 8 |  |  | no | clean trails in reservation?
3 | Essex St. | Fruit St. to Ware | 1 | 8 |  |  | no
3 | Ware St. | Essex to Short St | 0.5 | 6 |  |  | no | get area near stream
3 | East St. | Dustin Ct. to Norton Town line | 1.25 | 6 |  |  | no | includes North St.
3 | Mansfield Green | Inside the fence | 0 | 8 |  |  |  | group assigned
3 |  |  |  | 66
Precinct # | Street or Location | Boundaries | Distance in Miles | # of Volunteers Needed or Assigned | Assigned Group | Volunteers in Group | Safety Issue? | Notes
4 | Route 106 | Franklin St. to Easton Line | 1.5 | 16 | Knights of Columbus | 30 | yes
4 | Route 106 | Easton Line to Franklin St | 1.5 | 16 | Universalist Church | 40 | yes
4 | Stearns Ave | Erick Road to Mill Street | 1.25 | 12 |  |  | yes
4 | Maple Street | Franklin to Easton line | 1.5 | 10 |  |  | yes
4 | Stearns Ave | Stearns to Bonney to Erick Rd | 0.5 | 4 |  |  | no
4 | Winter St. | Franklin to Maple | 0.75 | 4 |  |  | yes
4 | Bird Road | Maple to Fram | 0.5 | 6 |  |  | no
4 | Patty's Road | under the power lines | 0.25 | 4
4 | Bonney Lane | Stearns to Bonney to Erick Rd | 0.5 | 4
76
Precinct # | Street or Location | Boundaries | Distance in Miles | # of Volunteers Needed or Assigned | Assigned Group | Volunteers in Group | Safety Issue? | Notes
5 | Route 106 | Route 140 To Foxboro Town line | 0.75 | 16 | Toyota & Smith & Nephew | 17 | yes | MEMA
5 | Route 106 | Copeland Drive to Train Station | 1 | 4 |  | 12 | yes
5 | Route 140 | 106 to Foxboro line | 0.5 | 35 | Boys Lacrosse team (Tim Frias)
5 | Route 140 | School St. to Route 106 | 1 | 18 | Mansfield Bank & Lagasse Sweet
5 | North Main St (downtown) | Route 106 to School St; includes Old Colony Way | 0.75 | 10 |  |  | no | this encompasses the main downtown area
5 | Rumford Ave | Old Colony Way to West St. (includes Fulton's Pond) | 0.5 | 6 |  |  | no | good for little kids
5 | Fulton's Pond area | Linda Mercier | 0 | 15 | Linda Mercier | 12 | no
5 | Copeland St | Foxboro line to West St. | 1 | 6 | Boy Scouts, Joe Milano |  | no | MEMA
5 | Train Station | Mansfield Ave down to North Common, including slope on route 106 | 0.5 | 8 | State Street | 6 | no
5 | Train Station | Winthrop St. Lot | 0.25 | 4 | State Street | 13 | no
5 | Train Station | River Street and parking lot | 0.25 | 8 | State Street | 15 | no
5 | County Street | Foxboro line to North Main | 0.5 | 6 | MMAS | 15 | yes
5 | West St. | Route 140 to Route 495 | 1 | 8 |  |  | yes | the area near West & Hampshire is pretty bad
5 | Plymouth St. | Plymouth to School | 0.5 | 4 |  |  | no
5 | Forbes Blvd | Route 140 to end of Cabot Blvd | 1 | 6 |  |  | no
5 | Giles Road | Route 106 to Copeland (includes Post Office) | 0.25 | 4 | Boy Scouts, Joe Milano |  | no
5 | Central St. | West St. to Foxboro line | 1 | 6 |  |  | no
5 | North Main St | County St/ to Foxboro line | 0.5 | 4 |  |  | no
5 | Forbes Blvd | Route 140 to Oxford Road | 0.75 | 6 |  |  | no
5 | Dubs liquors area | behind Lance Buick by VFW | 0.25 | 4
178
Precinct # | Street or Location | Boundaries | Distance in Miles | # of Volunteers Needed or Assigned | Assigned Group | Volunteers in Group | Safety Issue? | Notes
6 | Route 106 | Franklin to Hope Street (include pond at bridge near DPW) | 1 | 15 | Knights of Columbus |  | no
6 | Branch St | East St to Griffins Way | 0.5 | 6
6 | Pine Needle Lane | Franklin to end | 0.5 | 4
6 | East St. | route 106 to South Main | 1 | 6 |  |  | no | gully near Eddy st.is a mess
6 | Hope St. | Memorial Park to Swet Street | 0.75 | 25 | Cub Scouts |  | no | good for little kids; includes woods between Hope St. and Memorial Park Lot
6 | Franklin St. | Route 106 to Boundry | 1.5 | 8 |  |  | no | start on opposite ends
6 | Maple Street | Oakland to Franklin | 1.5 | 10 |  |  | yes
6 | Memorial Park | Library swamp and lower football field | 0.5 | 10 | Flag football (Jack Cooney) | 20 | no | good for little kids
6 | Memorial Park | tennis courts, skate park up to and including basketball courts; | 0.05 | 8 | Flag football (Jack Cooney) | 11 | no | good for little kids
6 | High School | lacrosse field, including perimeter of woods all the way to the track | 0.5 | 10 | Daisies/Brownies | 40 | no | good for kids; don't forget parking lot and section behind MHS gymnasium, up to the track.
6 | High School | rear parking lot of MHS/QMS, track, and woods behind track (on other side of fence) |  | 10 | Daisies/Brownies | 40 |  | good for little kids
6 | High School | Memorial Parking lot down to tennis courts, playground, softball field behind QMS, empty lot corner of Hope & Cottage | 0.5 | 10 | Daisies/Brownies |  | no | good for little kids
6 | QMS | entire perimeter of school property | 0.5 | 6 | Daisies/Brownies |  | no | good for little kids
6 | Jordan Jackson | gully in front of school | 0.5 | 10 |  | 35 | yes | good for little kids; boots and adult supervision needed; remove plastic bunting from creek side
6 | Jordan Jackson | woods on right side of entrance/fit trail | 0.5 | 6 | Daisies/Brownies | 35 | no | good for little kids
6 | Jordan Jackson | perimeter of J/J & Robinson lot, perimeter of woods in back, all around the school building | 0.5 | 10 | Daisies/Brownies | 35 | no | good for little kids
6 | Robinson School | perimeter of softball field, playground, perimeter of woods in back, woods to left of school | 0.5 | 8 | Daisies/Brownies | 35 | no | good for little kids
6 | Oakland Street | Foxboro line to Francis Ave, including Francis Ave. | 0.75 | 6 |  |  | no | start on opposite ends
6 | Oakland Street | Francis Ave to route 106 | 0.75 | 8 |  |  | no | start on opposite ends
6 | Francis Avenue | Maple to Oakland | 0.5 | 23 | Haunted Hollows (Pat Colbert)
199